## Product Backlog
Vision |  | Stock control system that will capture customer orders and update relevant stock items
EPICS/Themes | User story No. | User Stories : As a < type of user >, I want < some goal > so that < some reason > | Priority | Estimates (story points) | Sprint Iteration | Tasks
Login/Registration/Nav | 1 | As any user of the stock control system I want to be able to navigate to customer, supplier, stock or orders screen to carry out my daily work tasks and to be able to see pictures of the team and information about them. | 1 | 1 | Sprint 1
Customer component | 4 | As a user I need to be able to create a customer record so that I can maintain my customer details. | 2 | 3 | Sprint 1
Supplier component | 8 | As a user I need to be able to add suppliers to the system so that we can maintain supplier records | 3 | 3 | Sprint 1
Stock component | 11 | As a user I need to be able to add products to the system so that we can maintain product records | 4 | 3 | Sprint 1
Orders component | 15 | As a user I need to be able to order multiple products for a customer order so that I can place orders for customers of items that are currently in stock. | 5 | 8 | Sprint 1
Stock component | 14 | As a user I need to be alerted when stock runs below 5 on any stock item so that I can reorder stock. | 6 | 1 | Sprint 1
Orders component | 16 | As a user I need to be view the total cost of a customer order so that I can see money due. | 7 | 1 | Sprint 1
Customer component | 5 | As a user I need to be able to select a customer record to update so that I can maintain my customer details. | 8 | 2 | Sprint 1
Supplier component | 9 | As a user I need to be able to select a supplier record and update it so that I can maintain supplier records | 9 | 2 | Sprint 1
Stock component | 12 | As a user I need to be able to update products to the system so that we can maintain product records | 10 | 2 | Sprint 2
Orders component | 17 | As a user I can update the status of an order to maintain the order tracking. | 11 | 2 | Sprint 2
Customer component | 6 | As a user I need to be able to run customer reports so that I can view total sales by industry, area and sales person to monitor our sales. | 12 | 5 | Sprint 2
Customer component | 7 | As a user I need to be able to delete customer records so that I can maintain the system. | 15 | 1 | Sprint 2
Supplier component | 10 | As a user I need to be able to delete suppliers to the system so that we can maintain supplier records | 16 | 1 | Sprint 2
Stock component | 13 | As a user I need to be able to delete products to the system so that we can maintain product records | 17 | 1 | Sprint 2
|  | Total Points |  | 36
|  | Team Capacity |  | 24

## Sprint 1 Backlog
User Story No. | User Story | Story Points | Identified Tasks | Status | Owner | Hours remaining | Actual Time taken
1 | As any user of the stock control system I want to be able to navigate to customer, supplier, stock or orders screen to carry out my daily work tasks and to be able to see pictures of the team and information about them. | Navigate the system using buttons | Show buttons, implement button functionality, displaying pictures and descriptions of team members, exit the program | Done | Everyone
4 | As a user I need to be able to create a customer record so that I can maintain my customer details. | Add a customer record | Give fields to enter customer name, address and phone number and a button to create the customer and add it to the system | Done | Josh
8 | As a user I need to be able to add suppliers to the system so that we can maintain supplier records | Add a supplier record | Give fields to enter supplier name, address and phone number and a button to create the supplier and add it to the system | To do | Josh
11 | As a user I need to be able to add products to the system so that we can maintain product records | Add a product record | Enter product name, brand, stock and price and a button to create the supplier and add it to the system | Done | Tami
15 | As a user I need to be able to order multiple products for a customer order so that I can place orders for customers of items that are currently in stock. | Create an order using customer ID and product ID | Enter customer ID, product ID and amount of quantity to order and add it to the system | Done | Tami
14 | As a user I need to be alerted when stock runs below 5 on any stock item so that I can reorder stock. | Show warning when a products stock reaches beow 5 | After an order has been placed, check the products stock level to see if it is under 5 and show a warning | Done | Iuliana
16 | As a user I need to be view the total cost of a customer order so that I can see money due. | Show the total cost a customer is due | Enter a customer ID and calculate from each order they placed the total amount they have ordered | Done | Iuliana
5 | As a user I need to be able to select a customer record to update so that I can maintain my customer details. | Update a customer record | Select a customer record to update, show fields to edit and a button to submit changes | Done | George
9 | As a user I need to be able to select a supplier record and update it so that I can maintain supplier records | Update a supplier record | Select a supplier record to update, show fields to edit and a button to submit changes | Done | George

## Sprint 2 Backlog
User Story No. | User Story | Story Points | Identified Tasks | Status | Owner | Hours remaining | Actual Time taken
12 | As a user I need to be able to update products to the system so that we can maintain product records |  |  | To do | Tami
17 | As a user I can update the status of an order to maintain the order tracking. |  |  | To do | Tami
6 | As a user I need to be able to run customer reports so that I can view total sales by industry, area and sales person to monitor our sales. |  |  | To do | Josh
7 | As a user I need to be able to delete customer records so that I can maintain the system. |  |  | To do | Josh
10 | As a user I need to be able to delete suppliers to the system so that we can maintain supplier records |  |  | To do | Iuliana
13 | As a user I need to be able to delete products to the system so that we can maintain product records |  |  | To do | George

## Sprint 3 Backlog
User Story No. | User Story | Story Points | Identified Tasks | Status | Hours remaining | Actual Time taken

## Sheet2
0 | Sprint 1 | To do
1 | Sprint 2 | In progress
2 | Sprint 3 | Done
3
5
8
13